## Main Sheet
Tongariro Enterprises Ltd
GeT-HTML Project |  |  |  | Version: | 1.01
Project Members |  |  |  | Start Date | 2022-05-30
Position | Name | Email | Phone | End Date | 2022-10-31
Client | George | georget@whitecliffe.ac.nz
Client Rep | George | georget@whitecliffe.ac.nz
Project Manager/Coordinator | Anton | akuk211@mywhitecliffe.com | 022 0876050
Business Analyst | Andrea | abre201@mywhitecliffe.com | 022 475 3994
Finance | Zach | ztur211@mywhitecliffe.com | 021 085 73175
UX/UI Designer | Crystal | ccha201@mywhitecliffe.com | 021 708488
DevOps | Anton | akuk211@mywhitecliffe.com | 022 0876050
Senior Developer | Zach | ztur211@mywhitecliffe.com | 021 085 73175
Junior Developer | Crystal | ccha201@mywhitecliffe.com | 021 708488
Tester | Andrea | abre201@mywhitecliffe.com | 022 475 3994

## Budget
Tongariro Enterprises Ltd
Budget for GeT-HTML Project |  |  |  |  | Version: | 1.02
| Hours | $/h | Total | Notes | Total Budget | 100000
Project Manager/Coordinator | 260 | 43 | 11180 | 10h/week
Business Analyst | 10 | 63 | 630 | 10h - only for the handover
Finance | 26 | 45 | 1170 | 1h/week
UX/UI Designer | 60 | 37 | 2220 | 60h on an as needed basis
DevOps | 12 | 55 | 660 | 1.5h in the last 8 weeks
Senior Developer | 520 | 73 | 37960 | 20h/week
Junior Developer | 1000 | 30 | 30000 | 40h/week from week 7
Intermediate Developer | 300 | 45 | 13500 | 15h/week from week 7
Testers | 140 | 37 | 5180 | 10h/week from week 14
Software |  |  | 2068
Hardware |  |  | 7310
Total Costs |  |  | 111878
Software
Item | Price | Quantity | Total Cost | Notes
VPN | 708 | 1 | 708
Microsoft 365 | 340 | 4 | 1360
Total |  |  | 2068
Hardware
Item | Price | Quantity | Total Cost | Notes
PC | 800 | 4 | 3200 | Either new PC or upgrade CPU
NAS | 230 | 1 | 230
UPS | 280 | 1 | 280
Low-end/Refurbished Phones | 500 | 2 | 1000
High-end Phones | 1300 | 2 | 2600
Total |  |  | 7310

## Risk Register
Tongariro Enterprises Ltd
Risk Register for GeT-HTML Project | [11 empty] | Version: | 1.01
No. | Risk | Likelihood | Impact | Severity | Owner | Date | Mitigation | Impact | Severity | Action | Completion | Date | Comments
1 | If our budget allocation is incorrect, then there is a risk we can't afford certain things, and the project could remain unfinished until more funding is received |  |  |  | Project Manager | 2022-06-01 | Keep track of all costs each week and reevaluate budget allocation if unforseen circumstances occur
2 | The client does not like the product which is delivered |  |  |  | Project Co-ordinator | 2022-06-01 | Through using an agile approach, with meetings where the client is present, we will ensure we are on the same page. Decisions from the meeting will be documented to show the client's agreement throughout the development process
3 | If one of our staff members leave, then there is a risk that we won't have enough people to cover for the workload, and the project could fail to meet the deadline |  |  |  | Project Co-ordinator | 2022-05-30 | We will need to cover for their workload until we can bring in someone to take their place. Worst case scenario we can subcontract, outsource somebody
4 | The product doesn’t fit the market anymore. It leads to a sudden stop of work |  |  |  | Project Manager | 2022-06-01 | At the very beginning of a project, we conduct a discovery phase to learn more about the product, its purpose, and its functions.Our business analysts try to bring proper ideas and advice to clients on how to improve the product and bring more value to the end-users and market. They stay in close touch with Product Owners during the whole development process and help them to find the best solution if needed.
5 | If one of our staff members gets sick, then there is a risk that we won't have enough people to cover for the workload, and the project could fail to meet the deadline |  |  |  | Project Co-ordinator | 2022-05-30 | We will need to cover for their workload until they get better or/and we could plan for temp staff
6 | If our estimation for time taken to progress through the project is incorrect, there is a risk we don't get things done on time, and the project could fail to meet the deadline |  |  |  | Project Manager | 2022-05-30 | Each week get updates from team on where the project is at, and reevaluate if needed
7 | Underscoping the project. Some expectations from the clients may not have been understood in the business analysis phase. The expectation of the client might be for more features than communicated |  |  |  | Project Manager | 2022-06-01 | A brief with the scope and out of scope is given to the client. All decisions will be documented well
8 | If the control book is not completed by the deadline, there is a risk that the project will be delayed and will fail to meet the deadline |  |  |  | Project Manager | 2022-06-01 | Ensure to finish the control book, even if we need to work overtime
9 | Lack of leadership of the senior developer among the developers |  |  |  | Project Manager | 2022-06-01 | While the senior developer is a highly competent person, she is not the most assertive. The Project Manager will ensure that the senior developer is empowered and coaches her along the way
10 | Overlooking the "little" features and details |  |  |  | Project Manager | 2022-06-01 | The Project Manager will collect all the little features and requirement. The team will properly assess the story points and they will be added to the planning
11 | If there are changes to the scope of the project, there is a risk that our budget is used for nothing and the remaining budget is smaller than necessary |  |  |  | Project Manager | 2022-06-01 | Each week get updates from team on where the project is at, and reevaluate if needed
12 | If the software developer's computer breaks down, then there is a risk that we can't get any work done, and the project could fail to meet the deadline |  |  |  | Project Co-ordinator | 2022-05-30 | We will need to find an alternative way to get work done, such as getting a new computer, we will save the progress in github and commit every day
13 | If communication between the office and client are delayed, there is a risk this may have repercussions on the rest of the project and cause delays to the end result |  |  |  | Project Manager | 2022-06-01 | Delays will be expected, so we will need to work around these delays and plan ahead
14 | If during the development there are bugs that impact the project, there is a risk that the project will not work as planned, and will be received poorly by the customers |  |  |  | Developer | 2022-06-01 | Notify the team on what bugs have been found, and keep track of them, we will use TDD for development
15 | If none of our staff members have the skillset needed to complete a particular task, then there is a risk that we can't complete the project |  |  |  | Project Co-ordinator | 2022-06-01 | Employ someone who is capable of doing the job, enroll employees in training, or outsource the workload

## Gantt Chart
Create a Project Schedule in this worksheet. Enter title of this project in cell B1. Information about how to use this worksheet, including instructions for screen readers and the author of this workbook is in the About worksheet. Continue navigating down column A to hear further instructions. | Get <HTML>
Enter Company Name in cell B2. | Tongariro Enterprises Ltd
Enter the name of the Project Lead in cell B3. Enter the Project Start date in cell E3. Project Start: label is in cell C3. | By Aux Team | Project Start: |  | 2022-05-30
The Display Week in cell E4 represents the starting week to display in the project schedule in cell I4. The project start date is considered Week 1. To change the display week, simply enter a new week number in cell E4. The starting date for each week, starting with the display week from cell E4, starts in cell I4 and is auto calculated. There are 8 weeks represented in this view from cell I4 through cell BF4. You should not modify these cells. Display Week: label is in cell C4. |  | Display Week: |  | 1 |  |  | 2022-05-30 | [6 empty] | 2022-06-06 | [6 empty] | 2022-06-13 | [6 empty] | 2022-06-20 | [6 empty] | 2022-06-27 | [6 empty] | 2022-07-04 | [6 empty] | 2022-07-11 | [6 empty] | 2022-07-18 | [6 empty] | 2022-07-25 | [6 empty] | 2022-08-01 | [6 empty] | 2022-08-08 | [6 empty] | 2022-08-15 | [6 empty] | 2022-08-22 | [6 empty] | 2022-08-29
Cells I5 through BL5 contain the day number for the week represented in the cell block above each date cell and are auto calculated. You should not modify these cells. Today's date is outlined in Red (hex #AD3815) from today's date in row 5 through the entire date column to the end of the project schedule. | time axis 2022-05-30 to 2022-09-04
This row contains headers for the project schedule that follows below them. Navigate from B6 through BL 6 to hear the content. The first letter of each day of the week for the date above that heading, starts in cell I6 and continues through cell BL6. All project timeline charting is auto generated based on the start and end dates entered, using conditional formats. Do not modify content in cells within columns after column I starting with cell I7. | TASK | ASSIGNED TO | PROGRESS | START | END | DAYS | time axis 2022-05-30 to 2022-09-04
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
Cell B8 contains the Phase 1 sample title. Enter a new Title in cell B8. Enter a name to assign the phase to, if it applies for your project, in cell C8. Enter Progress for the entire phase, if it applies for your project, in cell D8. Enter the start and end dates for the entire phase, if it applies for your project, in cells E8 and F8. The Gantt chart will automatically fill in the appropriate dates and shade according to the progress entered. To delete the phase and work only from tasks, simply delete this row. | Phase 1 - Project setup, first designs, planning, documentation
Cell B9 contains the sample task "Task 1." Enter a new task name in cell B9. Enter a person to assign the task to in cell C9. Enter progress of the task in cell D9. A progress bar appears in the cell and is shaded according to the number in the cell. For example, 50 percent progress would shade half of the cell. Enter task start date in cell E9. Enter task end date in cell F9. A status bar shaded for the dates entered appears in blocks starting from cell I9 through BL9. | Task 1 : Budget calculations | Andrea Bredl | 100% | 2022-06-07 | 2022-06-10 | 4
Rows 10 through 13 repeat the pattern from row 9. Repeat the instructions from cell A9 for all task rows in this worksheet. Overwrite any sample data. A sample of another phase starts in cell A14. Continue entering tasks in cells A10 through A13 or go to cell A14 to learn more. | Task 2 : Budget calculations2 | Andrea Bredl | 100% | 2022-06-17 | 2022-06-24 | 8
| Task 3 : Risk register | Andrea Bredl, Zachariah James, Anton Kukharev, Chi Ling Crystal Chan | 50% | 2022-05-30 | 2022-06-19 | 21
| Task 4 : Logo design | Andrea Bredl | 100% | 2022-06-13 | 2022-06-17 | 5
| Task 5 : Research on competitors | Chi Ling Crystal Chan | 100% | 2022-06-07 | 2022-06-17
| Task 6 : Wireframes | Chi Ling Crystal Chan | 100% | 2022-06-13 | 2022-06-17
The cell at right contains the Phase 2 sample title. You can create a new phase at any time within column B. This project schedule does not require phases. To remove the phase, simply delete the row. To create a new phase block in this row, enter a new Title in cell at right. To continue adding tasks to the phase above, enter a new row above this one and fill in the task data as in cell A9's instruction. Update the Phase details in cell at right based on cell A8's instruction. Continue navigating down column A cells to learn more. If you haven't added any new rows in this worksheet, you will find 2 additional sample phase blocks have been created for you in cells B20 and B26. Otherwise, navigate through column A cells to find the additional blocks. Repeat the instructions from cells A8 and A9 whenever you need to. | Task 7 : Site map | Anton Kukharev | 100% | 2022-06-07 | 2022-06-18
| Task 8 : Color schema | Andrea Bredl | 100% | 2022-06-06 | 2022-06-13
| Task 9 : Fonts | Andrea Bredl | 100% | 2022-06-06 | 2022-06-19
| Task 10 : Control Book | Zachariah James | 100% | 2022-05-30 | 2022-06-13
| Task 11 : other documentation | Zachariah James, Anton Kukharev | 90% | 2022-05-30 | 2022-06-19
Sample phase title block | Phase 2 - Refining designs, customer approvals
| Task 1 : Risk register |  | 20% | 2022-06-20 | 2022-07-10 | 21
| Task 2 : Control Book |  | 50% | 2022-06-20 | 2022-07-10 | 21
| Task 3 : Change Register |  | 30% | 2022-06-20 | 2022-07-10 | 21
| Task 4 : Document register |  | 50% | 2022-06-20 | 2022-07-10 | 21
| Task 5 : Issues register |  | 50% | 2022-06-20 | 2022-07-10 | 21
This is an empty row | Phase 3 - Final designs, deployment
This row marks the end of the Project Schedule. DO NOT enter anything in this row. Insert new rows ABOVE this one to continue building out your Project Schedule. | Sprint 1 |  | 100% | 2022-06-21 | 2022-07-04 | 14
| Sprint 2 |  | 80% | 2022-07-05 | 2022-07-12 | 8
| Sprint 3 |  | 20% | 2022-07-15 | 2022-08-03 | 20
| Sprint 4 |  |  | 2022-08-04 | 2022-08-12 | 9
Refinement
| Production |  |  | 2022-08-15 | 2022-08-30 | 16
Insert new rows ABOVE this one

## Issues Register
Tongariro Enterprises Ltd
Issues Register for GeT-HTML Project | [8 empty] | Version: | 1.00
No. | Issue | Description | Reported by | Assigned to | Status | Priority | Date reported | Date resolved | Comment | Resolution
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20

## Lessons Learned Register
Tongariro Enterprises Ltd
Lessons Learned Register for GeT-HTML Project |  |  |  |  | Version: | 1.00
No. | Lesson | Description | Date | Owner | Sign off | Notes
1 | Learnt to budget according to the clients needs | We calculated the costs of staff and equipment, and the hours required to complete the project | 2022-07-08 | Financial Advisor
2 | Learnt to operate as a team in an Agile environment | We made use of a Kanban board and had regular meetings together on Teams | 2022-07-08 | Scrum Master
3 | Learnt how to cope with pressure from the client when the scope of the project has changed | We reallocated tasks to ensure we meet the new deadline | 2022-07-08 | All stakeholders
4 | Learnt how to work together exclusively online with different schedules | We used Teams daily to keep up to date with what was happening | 2022-07-08 | All stakeholders
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20

## Change Register
Tongariro Enterprises Ltd
Change Register for GeT-HTML Project | [7 empty] | Version: | 1.01
No. | Change | Owner | Date | Reason for Change | Action | Date | Resolution | Action | Notes
1 | Logo amended as per clients request | Client | 2022-06-10 | Client wanted the lightbulb symbol, as well as the away"HTML" was displayed | We updated the initial logo to show <HTML>, with the lightbulb beside it | 2022-06-13 | Logo changed | Logo changed
2 | Wireframe amended as per clients request | Client | 2022-06-16 | Client wanted to change the colour of the UI | We changed the colour of the UI to a light blue | 2022-07-10 | UI changed to light blue | UI changed to light blue
3 | Deadline changed to 10 August | Client | 2022-06-14 | Client wants to have it ready for Tech Week starting 17 August | We have adjusted our Budget and Gantt Chart according to what the client wants | 2022-07-18 | Budget increased by $12K | Budget increased by $12K
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19

## Benefits Register
Tongariro Enterprises Ltd
Benefits Register for GeT-HTML Project | Version: | 1.00

## Document Register
Tongariro Enterprises Ltd
Document Register for GeT-HTML Project |  |  |  |  | Version: | 1.04
No. | Name | Date | Filed | Who | Date | Comments
1 | Meeting Minutes May 23 | 2022-05-23 | v1.00 | Scrum Master
2 | Meeting Minutes May 28 | 2022-05-28 | v1.00 | Scrum Master
3 | Meeting Minutes June 3 | 2022-06-03 | v1.00 | Scrum Master
4 | Main Sheet | 2022-06-10 | v1.00 | Scrum Master
5 | Budget | 2022-06-10 | v1.00 | Scrum Master
6 | Gantt Chart | 2022-06-10 | v1.00 | Scrum Master
7 | Risk Register | 2022-06-10 | v1.00 | Scrum Master
8 | Documents Register | 2022-06-10 | v1.00 | Scrum Master
9 | Meeting Minutes June 10 | 2022-06-10 | v1.00 | Scrum Master
10 | Meeting Minutes June 16 | 2022-06-16 | v1.00 | Scrum Master
11 | Meeting Minutes June 23 | 2022-06-23 | v1.00 | Scrum Master
12 | Meeting Minutes June 27 | 2022-06-27 | v1.00 | Scrum Master
13 | Risk Register | 2022-07-04 | v1.01 | Scrum Master
14 | Gantt Chart | 2022-07-04 | v1.01 | Scrum Master
15 | Change Register | 2022-07-04 | v1.00 | Scrum Master
16 | Budget | 2022-07-04 | v1.01 | Scrum Master
17 | Main Sheet | 2022-07-08 | v1.01 | Scrum Master
18 | Budget | 2022-07-08 | v1.02 | Scrum Master
19 | Gantt Chart | 2022-07-08 | v1.02 | Scrum Master
20 | Lessons Learned Register | 2022-07-08 | v1.00 | Scrum Master
21 | Change Register | 2022-07-08 | v1.01 | Scrum Master

## (INFO) Risk Matrix
impact
|  | very low | low | medium | high | very high
likelihood | very high
high
medium
low
very low
Example for writing a Risk Statement
"If <event X> happens then there is a risk <consequence> that the project could be impacted in <Y way>"
| if [EVENT] |  | the new servers are not delivered by 10th February, then there is a risk that the
| [CONSEQUENCE] |  | commissioning engineers will not be able to start on the 11th and so there could be a
| [IMPACT] |  | delay to the project timeline

## Budget (Option 2)
Tongariro Enterprises Ltd
Budget (Option 2) for GeT-HTML Project |  |  |  |  | Version: | 1.01
| Hours | $/h | Total | Notes | Total Budget | 5500
Project Manager/Coordinator | 8 | 43 | 344 | Meet up with client for 3-4 times , between 1 to 2/h each time |  |  | Crystal | Second Option: | Only up to the click dummy, not actual app
Business Analyst | 10 | 63 | 630 | 10h - total project planning time
Finance | 15 | 45 | 675 | Full Project spend time
UX/UI Designer | 80 | 37 | 2960 | 80h - Design to end product
Software |  |  | 500
Total Costs |  |  | 5109
Software
Item | Price | Quantity | Total Cost | Notes
License | 160 | 1 | 160
Microsoft 365 | 340 | 1 | 340
Total |  |  | 500

## Budget (Option 3)
Tongariro Enterprises Ltd
Budget (Option 3) for GeT-HTML Project |  |  |  |  | Version: | 1.02
| Hours | $/h | Total | Notes | Total Budget | 100000
Project Manager/Coordinator | 10 | 43 | 430 | 10h/week
Business Analyst | 10 | 63 | 630 | 10h - only for the handover
Finance | 15 | 45 | 675 | 1h/week
UX/UI Designer | 60 | 37 | 2220 | 60h on an as needed basis
DevOps | 12 | 55 | 660
Senior Developer | 260 | 73 | 18980 | 10h/week
Junior Developer | 800 | 30 | 24000 | 40h/week
Intermediate Developer x 3 | 900 | 45 | 40500 | 15h/week
Testers | 140 | 37 | 5180 | 10h/week
Software |  |  | 2068
Hardware |  |  | 10710
Total Costs |  |  | 106053
Software
Item | Price | Quantity | Total Cost | Notes
VPN | 708 | 1 | 708
Microsoft 365 | 340 | 4 | 1360
Total |  |  | 2068
Hardware
Item | Price | Quantity | Total Cost | Notes
PC | 800 | 6 | 4800 | Either new PC or upgrade CPU
NAS | 230 | 1 | 230
UPS | 280 | 1 | 280
Low-end/Refurbished Phones | 500 | 3 | 1500
High-end Phones | 1300 | 3 | 3900
Total |  |  | 10710

## Gantt Chart (Option 2)
Create a Project Schedule in this worksheet. Enter title of this project in cell B1. Information about how to use this worksheet, including instructions for screen readers and the author of this workbook is in the About worksheet. Continue navigating down column A to hear further instructions. | Get <HTML>
Enter Company Name in cell B2. | Tongariro Enterprises Ltd
Enter the name of the Project Lead in cell B3. Enter the Project Start date in cell E3. Project Start: label is in cell C3. |  | Project Start: |  | 2022-05-30
The Display Week in cell E4 represents the starting week to display in the project schedule in cell I4. The project start date is considered Week 1. To change the display week, simply enter a new week number in cell E4. The starting date for each week, starting with the display week from cell E4, starts in cell I4 and is auto calculated. There are 8 weeks represented in this view from cell I4 through cell BF4. You should not modify these cells. Display Week: label is in cell C4. |  | Display week: |  | 1 |  | 2022-05-30 | [6 empty] | 2022-06-06 | [6 empty] | 2022-06-13 | [6 empty] | 2022-06-20 | [6 empty] | 2022-06-27 | [6 empty] | 2022-07-04 | [6 empty] | 2022-07-11
Cells I5 through BL5 contain the day number for the week represented in the cell block above each date cell and are auto calculated. You should not modify these cells. Today's date is outlined in Red (hex #AD3815) from today's date in row 5 through the entire date column to the end of the project schedule. | time axis 2022-05-30 to 2022-07-17
This row contains headers for the project schedule that follows below them. Navigate from B6 through BL 6 to hear the content. The first letter of each day of the week for the date above that heading, starts in cell I6 and continues through cell BL6. All project timeline charting is auto generated based on the start and end dates entered, using conditional formats. Do not modify content in cells within columns after column I starting with cell I7. | TASK | ASSIGNED TO | PROGRESS | START | END | time axis 2022-05-30 to 2022-07-17
Cell B8 contains the Phase 1 sample title. Enter a new Title in cell B8. Enter a name to assign the phase to, if it applies for your project, in cell C8. Enter Progress for the entire phase, if it applies for your project, in cell D8. Enter the start and end dates for the entire phase, if it applies for your project, in cells E8 and F8. The Gantt chart will automatically fill in the appropriate dates and shade according to the progress entered. To delete the phase and work only from tasks, simply delete this row. | Project setup, first designs, planning, documentation
Rows 10 through 13 repeat the pattern from row 9. Repeat the instructions from cell A9 for all task rows in this worksheet. Overwrite any sample data. A sample of another phase starts in cell A14. Continue entering tasks in cells A10 through A13 or go to cell A14 to learn more. | Budget calculations | Andrea Bredl | 100% | 2022-06-07 | 2022-06-10
| Risk register | Andrea Bredl, Zachariah James, Anton Kukharev | 60% | 2022-05-30 | 2022-06-19
| Logo design | Andrea Bredl | 100% | 2022-06-13 | 2022-06-17
| Research on competitors | Chi Ling Crystal Chan | 50% | 2022-06-07 | 2022-06-17
| Wireframes | Chi Ling Crystal Chan | 50% | 2022-06-13 | 2022-06-17
| Site map | Anton Kukharev | 0% | 2022-06-07 | 2022-06-18
| Color schema | Andrea Bredl | 0% | 2022-06-06 | 2022-06-13
| Fonts | Andrea Bredl | 0% | 2022-06-06 | 2022-06-19
| Control book | Zachariah James | 5% | 2022-05-30 | 2022-06-13
| other documentation | Zachariah James, Anton Kukharev | 5% | 2022-05-30 | 2022-06-19
The cell at right contains the Phase 2 sample title. You can create a new phase at any time within column B. This project schedule does not require phases. To remove the phase, simply delete the row. To create a new phase block in this row, enter a new Title in cell at right. To continue adding tasks to the phase above, enter a new row above this one and fill in the task data as in cell A9's instruction. Update the Phase details in cell at right based on cell A8's instruction. Continue navigating down column A cells to learn more. If you haven't added any new rows in this worksheet, you will find 2 additional sample phase blocks have been created for you in cells B20 and B26. Otherwise, navigate through column A cells to find the additional blocks. Repeat the instructions from cells A8 and A9 whenever you need to. | Refining designs, customer approvals
| Risk register |  | 80% | 2022-06-20 | 2022-07-10 | bar: 2022-06-20 to 2022-07-10
| Control book |  | 50% | 2022-06-20 | 2022-07-10
| Change Register |  |  | 2022-06-20 | 2022-07-10
| Document register |  |  | 2022-06-20 | 2022-07-10
| Issues register |  | 100% | 2022-06-20 | 2022-07-10
Sample phase title block | Delivery Timeline
| PDF/PS - Project 1st Draft | Zachariah James | 100% | 2022-06-10 | 2022-06-20
| Figma( Full design Broad) - Project 2st Draft | Chi Ling Crystal Chan | 50% | 2022-06-23 | 2022-07-08
| Figma( Interaction Prototype) | Anton Kukharev |  | 2022-07-11 | 2022-07-25
| Refinement(Final delivery) | Andrea Bredl |  | 2022-07-27 | 2022-08-02
This is an empty row
Note on W17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: =AND(H$9>=$E11,H$9<=$F11)

## Gantt Chart (Option 3)
Create a Project Schedule in this worksheet. Enter title of this project in cell B1. Information about how to use this worksheet, including instructions for screen readers and the author of this workbook is in the About worksheet. Continue navigating down column A to hear further instructions. | Get <HTML>
Enter Company Name in cell B2. | Tongariro Enterprises Ltd
Enter the name of the Project Lead in cell B3. Enter the Project Start date in cell E3. Project Start: label is in cell C3. |  | Project Start: |  | 2022-05-30
The Display Week in cell E4 represents the starting week to display in the project schedule in cell I4. The project start date is considered Week 1. To change the display week, simply enter a new week number in cell E4. The starting date for each week, starting with the display week from cell E4, starts in cell I4 and is auto calculated. There are 8 weeks represented in this view from cell I4 through cell BF4. You should not modify these cells. Display Week: label is in cell C4. |  | Display week: |  | 1 |  | 2022-05-30 | [6 empty] | 2022-06-06 | [6 empty] | 2022-06-13 | [6 empty] | 2022-06-20 | [6 empty] | 2022-06-27 | [6 empty] | 2022-07-04 | [6 empty] | 2022-07-11 | [6 empty] | 2022-07-18 | [6 empty] | 2022-07-25 | [6 empty] | 2022-08-01 | [6 empty] | 2022-08-08 | [6 empty] | 2022-08-15
Cells I5 through BL5 contain the day number for the week represented in the cell block above each date cell and are auto calculated. You should not modify these cells. Today's date is outlined in Red (hex #AD3815) from today's date in row 5 through the entire date column to the end of the project schedule. | time axis 2022-05-30 to 2022-08-21
This row contains headers for the project schedule that follows below them. Navigate from B6 through BL 6 to hear the content. The first letter of each day of the week for the date above that heading, starts in cell I6 and continues through cell BL6. All project timeline charting is auto generated based on the start and end dates entered, using conditional formats. Do not modify content in cells within columns after column I starting with cell I7. | TASK | ASSIGNED TO | PROGRESS | START | END | time axis 2022-05-30 to 2022-08-21
Cell B8 contains the Phase 1 sample title. Enter a new Title in cell B8. Enter a name to assign the phase to, if it applies for your project, in cell C8. Enter Progress for the entire phase, if it applies for your project, in cell D8. Enter the start and end dates for the entire phase, if it applies for your project, in cells E8 and F8. The Gantt chart will automatically fill in the appropriate dates and shade according to the progress entered. To delete the phase and work only from tasks, simply delete this row. | Project setup, first designs, planning, documentation
Rows 10 through 13 repeat the pattern from row 9. Repeat the instructions from cell A9 for all task rows in this worksheet. Overwrite any sample data. A sample of another phase starts in cell A14. Continue entering tasks in cells A10 through A13 or go to cell A14 to learn more. | Budget calculations | Andrea Bredl | 100% | 2022-06-07 | 2022-06-10
| Risk register | Andrea Bredl, Zachariah James, Anton Kukharev | 100% | 2022-05-30 | 2022-06-19
| Logo design | Andrea Bredl | 100% | 2022-06-13 | 2022-06-17
| Research on competitors | Chi Ling Crystal Chan | 100% | 2022-06-07 | 2022-06-17
| Wireframes | Chi Ling Crystal Chan | 100% | 2022-06-13 | 2022-06-17
| Site map | Anton Kukharev | 100% | 2022-06-07 | 2022-06-18
| Color schema | Andrea Bredl | 100% | 2022-06-06 | 2022-06-13
| Fonts | Andrea Bredl | 100% | 2022-06-06 | 2022-06-19
| Control book | Zachariah James | 100% | 2022-05-30 | 2022-06-13
| other documentation | Zachariah James, Anton Kukharev | 100% | 2022-05-30 | 2022-06-19
The cell at right contains the Phase 2 sample title. You can create a new phase at any time within column B. This project schedule does not require phases. To remove the phase, simply delete the row. To create a new phase block in this row, enter a new Title in cell at right. To continue adding tasks to the phase above, enter a new row above this one and fill in the task data as in cell A9's instruction. Update the Phase details in cell at right based on cell A8's instruction. Continue navigating down column A cells to learn more. If you haven't added any new rows in this worksheet, you will find 2 additional sample phase blocks have been created for you in cells B20 and B26. Otherwise, navigate through column A cells to find the additional blocks. Repeat the instructions from cells A8 and A9 whenever you need to. | Refining designs, customer approvals
| Risk register | Anton Kukharev | 80% | 2022-06-20 | 2022-07-10 | bar: 2022-06-20 to 2022-07-10
| Control book | Chi Ling Crystal Chan | 50% | 2022-06-20 | 2022-07-10
| Change Register | Chi Ling Crystal Chan | 50% | 2022-06-20 | 2022-07-10
| Document register | Zachariah James | 50% | 2022-06-20 | 2022-07-10
| Issues register | Anton Kukharev | 50% | 2022-06-20 | 2022-07-10
Sample phase title block | Interactive Prototype | Chi Ling Crystal Chan | 0% | 2022-07-27 | 2022-07-10 | bar: 2022-07-11 to 2022-08-10
Final designs, deployment | bar: 2022-07-11 to 2022-08-10
| Control book |  |  | 2022-07-11 | 2022-08-10
| Change Register |  |  | 2022-07-11 | 2022-08-10
| Document register |  |  | 2022-07-11 | 2022-08-10
This is an empty row | Issues register |  |  | 2022-07-11 | 2022-08-10
| Final Design |  |  | 2022-07-18 | 2022-08-10
| Tech Week |  |  |  | 2022-08-17
Note on W17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: =AND(H$9>=$E11,H$9<=$F11)

## Gantt Chart (OLD)
Tongariro Enterprises Ltd
Gantt Chart (OLD) for GeT-HTML Project |  | Version: | 1.00
2022-06-10
2022-06-11
2022-06-12
2022-06-13
2022-06-14

## Gantt Chart Data
Task No. | Start Date | End Date | Start on day | Duration | <-- NOTE: Need to enter data for gantt chart here
Control Book | 2022-05-30 | 2022-10-31 | 17 | 154 | Start on day & Duration columns are filled in automatically and are used for the chart to display correctly
Budget | 2022-05-30 | 2022-07-18 | 0 | 49
Risk Register | 2022-06-03 | 2022-07-20 | 4 | 47
Logo Design | 2022-06-16 | 2022-08-05 | 17 | 50
Wireframes | 2022-06-22 | 2022-08-22 | 23 | 61
Research on stack | 2022-07-11 | 2022-09-07 | 42 | 58
Development/Testing | 2022-08-30 | 2022-09-15 | 92 | 16
Final Testing | 2022-09-15 | 2022-10-01 | 108 | 16
User Testing | 2022-09-30 | 2022-10-31 | 123 | 31
Final adjustments/testing | 2022-09-30 | 2022-10-31 | 123 | 31
Deployment | 2022-10-20 | 2022-10-31 | 143 | 11